## Audit – Issues Found
# | Issue Type | Items Affected | Problem | Recommendation
1 | DUPLICATE | #7 + #21 | Both are 'Containerization' items with overlapping scope (Docker/K8s vs Dockerfile & Runtime). Two tickets for one task. | Merge into single item: 'Containerization – Dockerfile & docker-compose'. Drop #7.
2 | DUPLICATE | #30 + #31 + #33 | Three separate items for FHIR output (#30 Output Mapping to FHIR Standard, #31 FHIR Output Transformation, #33 Save FHIR JSON to disk). These are one feature. | Merge into single item: 'FHIR Output – Mapping & Persistence'. Code already exists in fhir_mapper.py + fhir_output_saver.py.
3 | DUPLICATE | #25 + #26 | Threaded PDF Processing – Per File (#25) vs Threaded Page Processing – Per Page (#26). Both exist in pdf_extractor.py already. | Merge into: 'Threaded Processing – Per-File & Per-Page'. Code exists, needs review not new development.
4 | MISPLACED | #2 Language Detection | Marked 'In Review' but shows 'Pending ¦ 10%'. A 10% complete item cannot be in review. Code exists in language.py and is functional. | Move to IN REVIEW at 80%. language.py + utils/language.py are implemented. Needs test coverage review.
5 | MISPLACED | #1 Relation Mapping | Marked 'In Review' but shows 'Pending ¦ 20%'. relation_mapper.py exists with full RelationMapper class. | Move to IN REVIEW at 70%. Code exists. Note says 'future batching required' – that's v2, not v1 blocker.
6 | MISPLACED | #3, #4 | Validation (#3) and Output Formatting (#4) both in 'In Review' at 30% but marked 'Pending'. Code exists for both. | Move to IN REVIEW at 70-80%. Both validator.py and output_formatter.py are implemented.
7 | MISSING | requirements.txt | No dependency file exists. Cannot deploy, cannot reproduce environment. This is a release blocker. | Add NEW item: 'Dependency Management – requirements.txt & pyproject.toml'. P0 priority.
8 | MISSING | FastAPI / REST API | #12 says 'In Progress ¦ 50%' but NO FastAPI code exists in the codebase. Zero lines. | Reset #12 to 0%. This is the largest remaining work item for v1.0.
9 | MISSING | CLI Interface | main.py has hardcoded Windows paths. No argparse/click. Unusable by anyone except the original developer. | Add NEW item: 'CLI Interface – argparse for main.py'. Required for v1.0.
10 | MISSING | Configuration Management | No YAML/JSON config, no .env, no settings module. All parameters hardcoded. | Add NEW item: 'Configuration – YAML config & environment variables'. Required before deployment.
11 | MISSING | Error Handling & Custom Exceptions | Only 9 try/except blocks, no custom exception classes. Print-based error reporting. | Add NEW item: 'Error Handling – Custom exceptions & error responses'. Required for API layer.
12 | MISSING | Integration Testing | #19 Pipeline Testing exists but no end-to-end integration test that simulates real document processing. | Add NEW item: 'Integration Testing – End-to-end document flow'. Required for release confidence.
13 | INFLATED % | #8 Core Engine 70% | main.py is 21 lines with hardcoded paths. 70% is not accurate for what a 'Core Engine' should be. | Reset to 30%. Needs CLI, config loading, proper error handling, and API server mode.
14 | INFLATED % | #10 OCR 60% | ocr.py and preprocess.py exist and work. But 60% undersells it – the OCR pipeline is more complete than that. | Raise to 80%. OCR extraction + preprocessing are functional. Needs edge case handling.
15 | SCOPE CREEP | #6 Deployment – Scalable Setup | Too vague for a v1.0 item. 'Scalable setup' implies K8s, load balancing, auto-scaling – that's v2+. | Rename to 'Deployment – Single-host Docker Setup'. Defer scaling to v2.

## V1.0 Kanban – Updated
ID | Task | Category | Status | Priority | Progress | Code Exists? | Depends On | V1.0 Required? | Expert Notes
#16 | Architecture – Modular Structure | Architecture | DONE | P0 – CRITICAL | 100% | Yes | — | Yes | Modular pipeline/ directory with clean separation. Foundation is solid. | Done
#24 | Unit Testing – OCR & NER | Testing | DONE | P1 – HIGH | 100% | Yes | — | Yes | test_ocr.py & test_ner.py in place. Good baseline. | Done
#32 | FHIR Mapping Tests – Pytest Conversion | Testing | DONE | P2 – MEDIUM | 100% | Yes | — | Yes | Converted to pytest assert format. Clean. | Done
#2 | Language Detection – langdetect module | Extraction | IN REVIEW | P1 – HIGH | 80% | Yes | — | Yes | MOVED from 10%→80%. language.py + utils/language.py fully implemented. Deterministic seeding. Needs: edge case tests for short text. | Done
#3 | Validation – Pydantic Schemas | Validation | IN REVIEW | P0 – CRITICAL | 80% | Yes | — | Yes | MOVED from 30%→80%. All 3 schemas implemented + @normalize_dates decorator. Needs: error message review for API consumers. | Done
#4 | Output Formatting – JSON Export | Output | IN REVIEW | P1 – HIGH | 80% | Yes | — | Yes | MOVED from 30%→80%. output_formatter.py works. Needs: configurable exclude_none behavior. | Done
#15 | Classification – PDF Type Detector | Extraction | IN REVIEW | P1 – HIGH | 80% | Yes | — | Yes | pdf_type_detector.py implemented. Threshold configurable. Needs: test with edge cases (encrypted PDFs, zero-page PDFs). | Done
#17 | Training – NER Pipeline (train_ner.py) | ML/NER | IN REVIEW | P2 – MEDIUM | 80% | Yes | #11 | No | Kanban says 80%. No train_ner.py file found. If training happens outside repo, document the workflow. Not blocking v1.0 if pre-trained models are loaded. | Done
#18 | Utils – language.py & text_utils.py | Utils | IN REVIEW | P2 – MEDIUM | 90% | Yes | — | Yes | Both files implemented and functional. Clean utilities. Ready to close after final review. | Done
#20 | Documentation – README & Developer Guide | Docs | IN REVIEW | P1 – HIGH | 70% | Yes | All | Yes | README.md exists and is comprehensive. Needs: API docs (once FastAPI exists), deployment guide, .env.example.
#23 | Output Schema Enforcement – Field Checks | Validation | IN REVIEW | P1 – HIGH | 75% | Yes | #3 | Yes | Pydantic schemas enforce field-level validation. Needs: custom error messages, field-level docs for API consumers. | Done
#25+26 | Threaded Processing – Per-File & Per-Page | Performance | IN REVIEW | P1 – HIGH | 85% | Yes | — | Yes | MERGED #25+#26. ThreadPoolExecutor in pdf_extractor.py (per-page) and process_folder.py (per-file). Sound architecture. Needs: thread count configurability. | Done
#27 | Thread-Safe Output Collector | Performance | IN REVIEW | P2 – MEDIUM | 70% | Partial | #25+26 | Yes | Results collected via futures and re-sorted by index. Pattern is correct. Needs: explicit error propagation from worker threads. | Done
#29 | Inference Engine – Model Routing | ML/NER | IN REVIEW | P0 – CRITICAL | 75% | Yes | #11 | Yes | inference.py has ModelBundle, ModelRegistry, InferenceEngine. Solid design. Needs: graceful handling when no model is registered for a document type. | Done
#30+31+33 | FHIR Output – Mapping & Persistence | Output | IN REVIEW | P1 – HIGH | 85% | Yes | #3, #4 | Yes | MERGED #30+#31+#33. fhir_mapper.py + fhir_output_saver.py both implemented. All 3 FHIR resource types mapped. Needs: output directory configurability. | Done
#1 | Relation Mapping – Entity Wiring | ML/NER | IN REVIEW | P2 – MEDIUM | 70% | Yes | #29 | Yes | MOVED from 20%→70%. relation_mapper.py has full RelationMapper class. 'Future batching' note is v2 scope. | Done
#9 | Ingestion – process_folder.py | Extraction | IN PROGRESS | P0 – CRITICAL | 80% | Yes | — | Yes | Functional with ThreadPoolExecutor. Needs: configurable input path (currently hardcoded), error handling for corrupt files, progress reporting. | Done
#10 | OCR & Preprocessing – ocr.py | Extraction | IN PROGRESS | P1 – HIGH | 80% | Yes | — | Yes | RAISED from 60%→80%. ocr.py + preprocess.py work. Needs: Tesseract language pack configuration, error handling for missing Tesseract. | Done
#11 | NER Modules – Prescription, Lab, Clinical | ML/NER | IN PROGRESS | P0 – CRITICAL | 50% | Partial | #29 | Yes | Schemas exist but actual NER model integration is incomplete. This is the core ML work. Needs: model files, loading logic, entity extraction pipelines. | Done
#8 | Core Engine – main.py Orchestration | Core | IN PROGRESS | P0 – CRITICAL | 30% | Partial | #9, #NEW-1 | Yes | LOWERED from 70%→30%. main.py is 21 lines with hardcoded paths. Needs: CLI args, config loading, API server mode, proper orchestration. | Done
#13 | Logging & Debug – Structured Logging | Infrastructure | IN PROGRESS | P1 – HIGH | 20% | Minimal | — | Yes | LOWERED from 60%→20%. Only 1 basic logger in fhir_output_saver.py. No structlog, no log config, no log levels. Needs full implementation. | Done
#14 | Testing – Unit & Module Tests | Testing | IN PROGRESS | P1 – HIGH | 60% | Yes | All modules | Yes | 17 test files, 758 LOC. Good coverage of validators, FHIR, formatters. RAISED from 40%→60%. Needs: OCR edge cases, API layer tests. | Done
#19 | Pipeline Testing – End-to-End | Testing | IN PROGRESS | P1 – HIGH | 30% | Partial | #9, #11 | Yes | test_pipeline.py exists (25 lines). Needs expansion: full document-in → JSON-out flow test. | Done
#12 | API Layer – FastAPI REST Endpoints | API | IN PROGRESS | P0 – CRITICAL | 0% | No | #8, #NEW-1 | Yes | RESET from 50%→0%. NO FastAPI code exists in codebase. Largest remaining work item. Needs: endpoint design, request/response models, file upload handling. | Done
#28 | Threaded Save & Export | Performance | IN PROGRESS | P3 – LOW | 40% | Partial | #25+26 | No | Output saving is synchronous but fast. Threading here is optimisation, not v1.0 requirement. Defer if time-constrained. | Done
NEW-1 | Dependency Management – requirements.txt | Infrastructure | NEW | P0 – CRITICAL | 0% | No | — | Yes | RELEASE BLOCKER. No requirements.txt or pyproject.toml. Cannot install, cannot deploy, cannot reproduce. Create immediately. | Done
NEW-2 | CLI Interface – argparse for main.py | Core | NEW | P0 – CRITICAL | 0% | No | #8 | Yes | main.py has hardcoded Windows paths. Add argparse with: --input-dir, --output-dir, --format (json/fhir/csv), --config, --log-level. | Done
NEW-3 | Configuration – YAML Config & .env | Infrastructure | NEW | P0 – CRITICAL | 0% | No | — | Yes | No config management exists. Create config.yaml for pipeline params + .env for secrets/paths. Use pydantic-settings or python-dotenv. | Done
NEW-4 | Error Handling – Custom Exceptions | Infrastructure | NEW | P1 – HIGH | 0% | No | — | Yes | Only 9 try/except blocks, print-based errors. Create exceptions.py with: DocumentExtractionError, ValidationError, ModelNotFoundError, OCRError. | Done
NEW-5 | API Models – Request/Response Schemas | API | NEW | P0 – CRITICAL | 0% | No | #12 | Yes | FastAPI needs Pydantic request/response models. DocumentUploadRequest, ProcessingResponse, ErrorResponse, HealthCheckResponse. | Done
NEW-6 | Integration Testing – Full Pipeline | Testing | NEW | P1 – HIGH | 0% | No | #12, #11 | Yes | No end-to-end test exists. Create: upload PDF → extract → validate → FHIR map → verify JSON output. Use test PDFs in data/Test/. | Done
NEW-7 | Public API Surface – __init__.py exports | Architecture | NEW | P2 – MEDIUM | 0% | No | — | Yes | All __init__.py files are empty. Define __all__ exports so consumers can: from dociq.pipeline import process_folder. | Done
NEW-8 | Health Check & Readiness Endpoints | API | NEW | P1 – HIGH | 0% | No | #12 | Yes | /health and /ready endpoints for Docker health checks and load balancer probes. Check Tesseract + model availability. | Done
#5 | Monitoring – Performance Logs & Metrics | Observability | BACKLOG | P3 – LOW | 0% | No | #13 | No | Prometheus metrics, Grafana dashboards. v2.0 scope. Structured logging (#13) is the v1.0 prerequisite. | Done
#6 | Deployment – Single-Host Docker Setup | DevOps | BACKLOG | P2 – MEDIUM | 0% | No | #21, NEW-1 | No | RENAMED from 'Scalable Setup'. Single docker-compose with app + optional Mosquitto. K8s/scaling is v2.0. | Done
#21 | Containerization – Dockerfile & Runtime | DevOps | BACKLOG | P2 – MEDIUM | 10% | No | NEW-1, #12 | No | Dockerfile with Python 3.10+, Tesseract, Poppler. #7 merged into this. Deferred: needs working API first. | Done
#22 | Model Loading & Saving – NER/Classifier/OCR | ML/NER | BACKLOG | P2 – MEDIUM | 0% | No | #11 | No | Model serialization and hot-reloading. ModelBundle supports lazy loading already. Enhance when model artifacts are stable. | Done

## V1.0 Release Checklist
# | Milestone | Tasks Included | Status | Target | Exit Criteria
1 | M1: Infrastructure Foundation | NEW-1 (requirements.txt), NEW-3 (config), NEW-4 (exceptions) | NOT STARTED | Week 1 | pip install -r requirements.txt works. Config loads from YAML. Custom exceptions importable.
2 | M2: Core Engine Rewrite | #8 (main.py), NEW-2 (CLI), #13 (logging) | NOT STARTED | Week 1-2 | python -m dociq --input-dir ./data --output-dir ./output --format fhir runs successfully. Structured logs to stdout.
3 | M3: Extraction Pipeline Closure | #9 (ingestion), #10 (OCR), #2 (language), #15 (PDF type) | IN PROGRESS | Week 2 | All 4 extraction components pass unit tests. Configurable paths. Error handling for corrupt/missing files.
4 | M4: NER & Inference Completion | #11 (NER modules), #29 (inference engine), #1 (relation mapper) | IN PROGRESS | Week 2-3 | InferenceEngine processes all 3 document types. Models load from configurable path. Graceful fallback when model missing.
5 | M5: Validation & Output | #3 (validation), #4 (formatting), #23 (schema enforcement), #30+31+33 (FHIR) | IN REVIEW | Week 3 | All outputs pass schema validation. FHIR JSON matches resource spec. Output directory configurable.
6 | M6: API Layer | #12 (FastAPI), NEW-5 (API models), NEW-8 (health check) | NOT STARTED | Week 3-4 | POST /process accepts PDF upload, returns structured JSON. GET /health returns 200. OpenAPI docs at /docs.
7 | M7: Testing & Quality | #14 (unit tests), #19 (pipeline tests), NEW-6 (integration) | IN PROGRESS | Week 4 | All tests pass. Integration test: PDF upload → API → structured JSON verified. Coverage > 70%.
8 | M8: Documentation & Packaging | #20 (README), NEW-7 (__init__.py), NEW-1 (deps) | IN REVIEW | Week 4-5 | README has quickstart, API docs, .env.example. Package installable via pip install -e . Clean imports.
9 | M9: Containerization (Optional v1.0) | #21 (Dockerfile), #6 (deployment) | BACKLOG | Week 5+ | docker-compose up starts API server. Health check passes. Tesseract + Poppler pre-installed in image.

## Summary
DocIQ v1.0 – Kanban Audit Summary
ORIGINAL KANBAN | UPDATED KANBAN | DELTA
Total items | 33
Duplicates found |  | 6 items → 3 merged
Misplaced items |  | 5 items repositioned
Missing items (NEW) |  | 8 items added
Items with inflated % |  | 4 items corrected
UPDATED COUNTS | Count | V1.0 Required
DONE | 3 | 3
IN REVIEW | 13 | 12
IN PROGRESS | 9 | 8
NEW (expert-added) | 8 | 8
BACKLOG (deferred) | 4 | 0
TOTAL | 0 | 0
V1.0 RELEASE ESTIMATE
Remaining work items | 28 |  | Items that need work before release
Estimated weeks | 4-5 |  | Assumes 1 developer, full-time. Parallel tracks possible.
Biggest risk |  |  | NER model integration (#11) – core ML work with uncertain scope
Fastest win |  |  | NEW-1 (requirements.txt) + NEW-3 (config) – 1 day, unblocks everything